## Sheet1
Roadmap for tBB
					Daniele Parmeggiani for Doxee, 13/07/2016

It is necessary to point out that each of these steps does require its own unittests.

Date of Start	Date of End	Actual Date of Start	Actual Date of End	Description					Stage
12/07/2016	12/07/2016	12/07/2016	12/07/2016	Base IP, Network and Host Python representation.
13/07/2016	14/07/2016	13/07/2016		Specifications document write-out & discussion (?).
13/07/2017	14/07/2016	13/07/2019		Logger implementation.
14/07/2016	14/07/2017	14/07/2016		Main service command line interface implementation.
				ICMP discovery implementation.
				ARP discovery implementation.
				SYN discovery implementation.
				Serialization mechanism implementation.
				Notification mechanism implementation.
				Tracker implementation.					α1
				Built-in notifiers implementation.
				Back-end handler implementation.
				Built-in CLI back-end implementation.					α2
				Built-in web back-end implementation.					β
				Final tests & bugfixes.					RC