## Sheet1
Roadmap for tBB
					Daniele Parmeggiani for Doxee, 13/07/2016

It is necessary to point out that each of these steps does require its own unittests.

Date of Start	Date of End	Actual Date of Start	Actual Date of End	Description					Stage
12/07/2016	12/07/2016	12/07/2016	12/07/2016	Base IP, Network and Host Python representation.
13/07/2016	--	13/07/2016	ongoing	Specifications document write-out & discussion (?).
13/07/2016	14/07/2016	13/07/2016	14/07/2016	Logger implementation.
14/07/2016	14/07/2016	14/07/2016	14/07/2016	Main service command line interface implementation.
14/07/2016	15/07/2016	14/07/2016	15/07/2016	ICMP discovery implementation.
14/07/2016	15/07/2016	14/07/2016	15/07/2016	ARP discovery implementation.
14/07/2016	15/07/2016	14/07/2016	15/07/2016	SYN discovery implementation.
18/07/2016	19/07/2016			Serialization mechanism implementation.
20/07/2016	20/07/2016			Notification mechanism implementation.
21/07/2016	25/07/2016			Tracker implementation.					α1
26/07/2016	26/07/2016			Built-in notifiers implementation.
27/07/2016	29/07/2016			Back-end handler implementation.
01/08/2016	03/08/2016			Built-in CLI back-end implementation.					α2
03/08/2016	09/08/2016			Built-in web back-end implementation.					β
10/08/2016	11/08/2016			Final tests & bugfixes.					RC